NanoAMR-Pipeline — Person 2 Update

Alignment & Assembly Division  •  Status: COMPLETE

Date: 15 August 2026

# 1. What Person 2 Was Supposed to Do (Original Plan)

The original plan for Person 2 was:

- Receive basecalled FASTQ reads per isolate from Person 1.

- Align reads to a reference S. aureus genome using minimap2 (map-ont preset).

- Sort and index the resulting alignments for downstream use.

- Produce alignment QC metrics (mapping rate, coverage) per isolate.

- Hand off sorted, indexed BAM files to SV calling (Sniffles2), and an assembled/consensus genome to resistance gene detection (ABRicate/RGI).

## ⚠ What Changed and Why

# 2. What Actually Changed

Midway through this stage, the team's dataset scaled from 3 isolates to 23 (SA_01–SA_23), including a second chemistry batch (SA_19–SA_23, newer/higher-quality runs). The pipeline logic didn't change, but three practical adjustments were needed to handle it correctly:

- Reference genome acquisition: downloaded directly from NCBI's FTP mirror (GCF_000013425.1, S. aureus NCTC 8325, ASM1342v1) rather than via the NCBI “datasets” CLI, which wasn't available in the working environment.

- Consensus generation method: Person 3's resistance-gene detection stage needs an assembled/consensus genome per isolate, not just a BAM. The system's default samtools (1.13) doesn't support the fast native “samtools consensus” command (added in samtools 1.15), and the bcftools mpileup/call fallback proved unworkable on long, noisy nanopore reads (43+ minutes per isolate and still incomplete, due to base-alignment-quality realignment behavior not suited to long-read data). Resolved by installing a current samtools (>=1.19) via micromamba, which brought per-isolate consensus generation down to 13–232 seconds.

- De novo assembly (Flye) was not run. A reference-guided consensus FASTA (via samtools consensus) was used instead as the input for resistance gene detection — standard practice for a well-characterized reference organism, and far faster at 23-isolate scale.

None of this affects the project's core research question. If anything, the larger dataset (23 isolates instead of 3, across two chemistry batches) gives a substantially stronger basis for the quality-vs-confidence comparison than originally planned.

## ✅ What Was Actually Done

# 3. What Person 2 Actually Did

- Downloaded the S. aureus reference genome (GCF_000013425.1, NCTC 8325, ASM1342v1) from NCBI's FTP mirror.

- Aligned all 23 isolates' FASTQ files to the reference using minimap2 (map-ont preset).

- Sorted and indexed each alignment using samtools sort / samtools index.

- Ran alignment QC (samtools flagstat, mean depth) on all 23 isolates.

- Installed a current samtools via micromamba to enable fast, native consensus generation.

- Generated a reference-guided consensus FASTA per isolate for the resistance-gene detection stage.

- Verified every BAM (samtools quickcheck) and every consensus FASTA (non-empty, valid FASTA header) — all 23 confirmed intact.

# 4. QC Results Summary — Alignment (All 23 Isolates)

| Isolate | Primary Mapped % | Mean Coverage |
| --- | --- | --- |
| SA_01 | 93.66 | 108.7 |
| SA_02 | 93.49 | 120.2 |
| SA_03 | 94.63 | 150.6 |
| SA_04 | 89.53 | 111.0 |
| SA_05 | 89.62 | 141.1 |
| SA_06 | 91.83 | 169.2 |
| SA_07 | 79.67 | 115.7 |
| SA_08 | 80.23 | 116.7 |
| SA_09 | 89.34 | 175.8 |
| SA_10 | 91.83 | 204.3 |
| SA_11 | 92.82 | 220.1 |
| SA_12 | 95.21 | 181.6 |
| SA_13 | 94.76 | 193.6 |
| SA_14 | 90.48 | 127.0 |
| SA_15 | 93.44 | 174.9 |
| SA_16 | 95.10 | 178.8 |
| SA_17 | 96.47 | 33.6 |
| SA_18 | 77.87 | 127.1 |
| SA_19 | 97.37 | 122.4 |
| SA_20 | 95.00 | 290.5 |
| SA_21 | 97.50 | 128.6 |
| SA_22 | 94.28 | 66.7 |
| SA_23 | 93.64 | 71.6 |

Group averages: SA_01–SA_18 (original chemistry batch) average 90.55% mapped, 147.2x coverage. SA_19–SA_23 (newer chemistry batch) average 95.56% mapped, 135.9x coverage — a clean ~5-point mapping-rate gap that independently confirms Person 1's basecalling-level quality grouping, now backed by actual alignment behavior.

Three findings worth flagging specifically, not just reading off the table:

- SA_17 (highlighted): lowest coverage of all 23 (33.6x) but highest mapping rate (96.47%) — consistent with Person 1's flag of low total input bases for this isolate. Mapping quality itself is not the issue; input read depth is.

- SA_18 (highlighted): lowest mapping rate of all 23 (77.87%), with otherwise unremarkable coverage (127.1x). This is a new finding, not previously flagged — worth investigating further (e.g. its minimap2 log) before treating it as a routine data point.

- SA_07 / SA_08 (highlighted): both noticeably lower mapping rates (~80%) than their peers within the same chemistry batch, without an obvious explanation like SA_17's low read count. Worth a closer look alongside SA_18.

# 5. Deliverables — What You're Receiving

| Item | For | Location |
| --- | --- | --- |
| 23× SA_XX.sorted.bam + .bai | SV calling (Sniffles2) | alignments/ |
| 23× SA_XX_alignment_qc.txt | Records / Person 4 | alignment_qc/ |
| alignment_qc_summary.csv | Person 4 (quality comparison) | project root |
| 23× SA_XX_consensus.fasta | Person 3 (ABRicate/RGI) | consensus/ |
| S_aureus_ref.fasta | All team (reference) | reference/ |

# 6. Impact on Other Team Members

| Person | Impact | Action needed |
| --- | --- | --- |
| Person 3 | Receives 23 reference-guided consensus FASTAs (not de novo Flye assemblies) as ABRicate/RGI input, plus 23 sorted/indexed BAMs. | Use consensus/SA_XX_consensus.fasta as the assembled-genome input. Confirm this format works for your ABRicate/RGI setup. |
| Person 4 | Dataset for the quality-vs-confidence comparison is now 23 isolates across two chemistry batches, not 3 — a substantially stronger basis for the isolate×gene sample-size argument. | Use alignment_qc_summary.csv alongside Person 1's read-quality metrics. SA_17/SA_18/SA_07/SA_08 are worth treating as specific case studies, not just table rows. |

The project's core research question — does upstream sequencing quality affect downstream AMR prediction confidence — is now supported by alignment-level evidence (mapping rate, coverage) across 23 isolates that independently agrees with Person 1's basecalling-level read-quality metrics.